## Sayfa1
Nr | Component | Issue Type | Issue Title | URL | Steps To Reproduce | Expected Result | Actual Result | Screenshot | Video
1 | SEARCH BAR | Visual | "Image not found" is displayed when clicking on SEARCH BAR in main page and typing some of products | https://qatest-dev.indvp.com/ | 1) Open the site https://qatest-dev.indvp.com/ 2) Click on search bar 3) Type the product | Seeing images correctly | "Image not found" error | https://ibb.co/SBcpVNR | https://www.loom.com/share/aa8382d1085c4dfa9c1aff01c461d26c
2 | MAIN PAGE | Visual | There is no 'home page' button | https://qatest-dev.indvp.com/ | 1)Open home page | There is a 'home page' button on the top | There is no any button about 'home page' | https://ibb.co/8dj2bCj | https://www.loom.com/share/dd306148827c49259960fc2ee7c63d8c
3 | BED & BATH | Functional | when the page opened it gets the error : "404 page not found" | https://qatest-dev.indvp.com/collections/bed-bath?___store=default | 1) Open the site https://qatest-dev.indvp.com/ 2)click on Bed & Bath page | Correctly opened Bed & Bath page | Getting "404 page not found" error | https://ibb.co/n898cVR | https://www.loom .com/share/ddd 66580393f4473a bc768e571fe2ca4
4 | CONTACT US | Functional | when the page opened it gets the error : "404 page not found" | https://qatest-dev.indvp.com/contacts | 1) Open the site https://qatest-dev.indvp.com/ 2)click on Contact Us page | Correctly opened Contact Us page | Getting "404 page not found" error | https://ibb.co/4Nd5zfY | https://www.loom .com/share/2809 5751b86149eeaa 5ff709373da488
5 | REFUNDS | Functional and Visual | when the page opened it gets the error : "404 page not found" | https://qatest-dev.indvp.com/catalog-request | 1) Open the site https://qatest-dev.indvp.com/ 2)click on Returns page | Correctly opened Refunds page and also typed Returns | Getting "404 page not found" error | https://ibb.co/4Nd5zfY | https://www.loom .com/share/1fb36 638930847df97f6 e647badbe59f
6 | CATALOGUE-REQUEST | Functional | after typing the invalid spaces and clicking on send button it returns "Internal Server Error" | https://qatest-dev.indvp.com/faqs | 1)Open the site 2)Click on catalogue request 3)Fill invalid spaces 4)Click on Send button | A massage about user sending his or her request correctly | Returns "Internal Server Error" | https://ibb.co/tC0PLzw | https://www.loom .com/share/9f221 261a3f54261ae4 232ab5127d85e
7 | SALE ROOM | Functional | when the page opened it gets the error : "404 page not found" | https://qatest-dev.indvp.com/sale-room | 1) Open the site https://qatest-dev.indvp.com/ 2)click on Sale Room page | Correctly opened Sale Room page | Getting "404 page not found" error | https://ibb.co/4Nd5zfY | https://www.loom.com/share/c4db43587bd441eb9810fec3e86484a1
8 | GIFT FOR THE GARDENERS | Functional | when the page opened it gets the error : "404 page not found" | https://qatest-dev.indvp.com/gifts-45/gifts-for-gardeners | 1) Open the site https://qatest-dev.indvp.com/ 2)click on Gift for the Gardeners page | Correctly opened Gift for the Gardeners page | Getting "404 page not found" error | https://ibb.co/4Nd5zfY | https://www.loom.com/share/cd8ad1eb7d714729abe7a32c7dc6e858
9 | WEDDING GIFTS | Functional | when the page opened it gets the error : "404 page not found" | https://qatest-dev.indvp.com/gifts-45/wedding-gifts | 1) Open the site https://qatest-dev.indvp.com/ 2)click on Wedding Gifts page | Correctly opened Wedding Gifts page | Getting "404 page not found" error | https://ibb.co/4Nd5zfY | https://www.loom .com/share/d057 2cdc2978419ab13 3493fb8feebbf
10 | KITCHEN TEXTILES | Functional | when the page opened it gets the error : "404 page not found" | https://qatest-dev.indvp.com/kitchen-dining/kitchen-textiles | 1) Open the site https://qatest-dev.indvp.com/ 2)click on Kitchen Textiles page | Correctly opened Kitchen Textiles page | Getting "404 page not found" error | https://ibb.co/4Nd5zfY | https://www.loom .com/share/132f3 0d8fdec4f4e8e52 6537497a3a9f
11 | CANDLES | Functional | when the page opened it gets the error : "404 page not found" | https://qatest-dev.indvp.com/portmeirion/candles | 1) Open the site https://qatest-dev.indvp.com/ 2)click on Candles page | Correctly opened Candles page | Getting "404 page not found" error | https://ibb.co/4Nd5zfY | https://www.loom.com/share/5153b073745e47c592590e2e4636acb0
12 | VIEW CART | Functional | when clicked on the view cart it gets the error: "Ooops! Something went wrong!" | https://qatest-dev.indvp.com/cart | 1) Open the site https://qatest-dev.indvp.com/ 2)click on View Cart page | Correctly opened View Cart | Getting "Ooops! Something went wrong!" error | https://ibb.co/ysKb9k2 | https://www.loom.com/share/1dae93d2cade41ef929151ca22d631cf